## 2026
|  | May 26 Sprint 1 | [12 empty] | May 26 Sprint 2 | [12 empty] | June 26 Sprint 1 - TBD | [12 empty] | June 26 Sprint 2 | [12 empty] | July 26 Sprint 1 | [12 empty] | July 26 Sprint 2 | [12 empty] | Aug 26 Sprint 1 | [12 empty] | Aug 26 Sprint 2 | [12 empty] | Sep 26 Sprint 1 | [12 empty] | Sep 26 Sprint 2 | [12 empty] | Oct 26 Sprint 1 | [12 empty] | Oct 26 Sprint 2 | [12 empty] | Nov 26 Sprint 1 | [12 empty] | Nov 26 Sprint 2 | [12 empty] | Dec 26 Sprint 1 | [12 empty] | Dec 26 Sprint 2
Activity |  | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Daniel N | Muchtar | Adi | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Daniel N | Muchtar | Adi | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal | Dror | Miri | Maor | Shachar | Ariel R | Sarah | Stav | Tony | Don | Muchtar | Adi | Daniel N | Igal
TOTAL EMPLOYEE CAPACITY PER SPRINT >>>>>> |  | 110% | 85% | 125% | 100% | 100% | 65% | 110% | 35% | 0% | 105% | 0% | 50% | 100% | 110% | 80% | 90% | 100% | 100% | 50% | 55% | 50% | 80% | 0% | 85% | 70% | 95% | 110% | 100% | 85% | 100% | 100% | 50% | 60% | 50% | 55% | 120% | 0% | 85% | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Adapt global studios (AI Assess) | 10% | [32 empty] | 10%
Administration (HRS,Hubspot, Etc) | 50% | [6 empty] | 50%
AI and Presell | 5% | [5 empty] | 5%
Aires (AI Assess RAPID) | 40% | [20 empty] | 20% | [12 empty] | 20%
Einat Asic [Mishki Ram] - SW Discovery | 120% | [23 empty] | 30% | [13 empty] | 30% | [11 empty] | 30% | [12 empty] | 30%
Black widow - (signed on nov 25 ) | 60% | [19 empty] | 30% | [12 empty] | 30%
Black Widow MVP (16.01) | 30% | [6 empty] | 30%
BMT | 5% | [6 empty] | 5%
CBC (T&M) | 20% | [25 empty] | 10% | [12 empty] | 10%
Ceel | 10% | [12 empty] | 10%
Elcam - Delivery | 15% |  | 15%
FuturePACS assess | 30% | [25 empty] | 15% | [12 empty] | 15%
HRS | 15% |  | 5% | [12 empty] | 5% | [12 empty] | 5%
Hyp | 30% | 10% | [12 empty] | 10% | [12 empty] | 10%
IAI (POC) - 23 hr | 20% | [21 empty] | 20%
IBI Roeto MVP | 30% | [9 empty] | 10% | [14 empty] | 10% | [10 empty] | 10%
IBI searchfund MVP | 15% | [21 empty] | 15%
IBI Transactions MVP | 15% | [21 empty] | 15%
Lake (MVP) | 20% |  |  | 20% | [12 empty] | 0% | [12 empty] | 0%
Mishki Ram - Barak [3.11] | 5% | [9 empty] | 5%
Rimon - Mishki Ram - Raam (Water Dev) | 0%
OptionUp POC | 45% | [7 empty] | 15% | [12 empty] | 15% | [12 empty] | 15%
Partner Prod (20 hrs PM) | 0%
Patient7 ($125K MVP) | 45% |  |  | 15% | [12 empty] | 15% | [12 empty] | 15%
Paz Gaz | 140% |  |  | 20% |  |  | 5% | 25% | [8 empty] | 25% |  |  | 0% | 25% | [8 empty] | 20% |  |  | 0% | 20%
Presale | 5% |  | 5%
ProjectTools ($31K POC) | 0%
RodRadar | 155% |  | 30% | [12 empty] | 50% | [12 empty] | 75%
Septier | 150% | [5 empty] | 50% | [12 empty] | 50% | [12 empty] | 50%
SignetureDX | 300% | 100% | [12 empty] | 100% | [12 empty] | 100%
Smart Girls PoC | 45% | [7 empty] | 15% | [12 empty] | 15% | [12 empty] | 15%
Subivi (AI Assess) | 0%
SuperPharm (BO) | 150% |  |  | 50% | [12 empty] | 50% | [12 empty] | 50%
SuperPharm (Pharmacy) | 300% |  |  |  | 100% | [12 empty] | 100% | [12 empty] | 100%
SuperPharm (POS) | 300% |  |  |  |  | 100% | [12 empty] | 100% | [12 empty] | 100%
Tadiran | 75% |  | 30% | [12 empty] | 25% | [12 empty] | 20%
Leadbeam (PoC) | 0%
GradIT PoC | 5% | [7 empty] | 5% | [12 empty] | 0% | [12 empty] | 0%
Leumit OCR - Presale | 0%
Lightship - MVP | 90% | [9 empty] | 30% | [14 empty] | 30% | [10 empty] | 30%
Linkme POC | 10% | [9 empty] | 10% | [25 empty] | 0%
BuyerFolio (PoC) | 0%
Eduard Technologies (TWO PoCs) | 0%
Open University | 100% | [11 empty] | 25% | [11 empty] | 25% | [10 empty] | 25% |  |  | 25%
Seacure ZEN | 5% |  |  | 0% |  |  | 5% | [9 empty] | 0% | [12 empty] | 0%
ImmuniSense PoC | 45% | [12 empty] | 15% | [12 empty] | 15% | [12 empty] | 15%
BIO Catch Discovery | 0%
VCOMM POC | 0%
Investmint POC | 0%
Malmab | 60% | [21 empty] | 30% | [12 empty] | 30%
Averna (assesment) | 0%
Flexfactor MVP | 45% | [9 empty] | 15% | [25 empty] | 30%
Benchmark MVP | 90% | [9 empty] | 30% | [14 empty] | 30% | [10 empty] | 30%
Ryvid MVP signed 31/3 | 90% | [12 empty] | 30% | [12 empty] | 30% | [12 empty] | 30%
ScyllaDB (sw) | 0%
Energyby5 | 30% | [12 empty] | 10% | [12 empty] | 10% | [12 empty] | 10%
LayerX Assess 9/4 | 0%
Pandos Assess (8.04) | 0%
Seeded Assess (10.4) | 0%
FuturePACS PoC | 0%
StoreNext | 50% | [9 empty] | 5% |  | 25% | [23 empty] | 20%
Greywolf AI POC ( signed - 27.4.26) | 30% | [12 empty] | 15% | [12 empty] | 15%
DBdude | 0%
Vivaium - SW Discovery | 20% |  |  | 20%
CryptoC (SW) | 180% | [23 empty] | 30% | [13 empty] | 30% | [11 empty] | 30% | [12 empty] | 30% | [12 empty] | 30% | [12 empty] | 30%
Rezora AI Assess 5K | 10% | [12 empty] | 10%
Flexible AI Assess (14.4) | 10% | [12 empty] | 10%
Note on L20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A per Daniel. 4 sprints. 10%. Started at April 01
Note on AA20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A per Daniel. 4 sprints. 10%. Started at April 01
Note on AL20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A per Daniel. 4 sprints. 10%. Started at April 01
Note on L24: Dror Shem-Tov: סיום תחילת מאי
Note on H29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As per Daivid on whatsapp 10% at the most - till end of June
Note on U29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As per Daivid on whatsapp 10% at the most - till end of June
Note on AH29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As per Daivid on whatsapp 10% at the most - till end of June
Note on D30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adler homski presale